## Sheet1
Sl No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | 20-11-2025 | Database seeding failed for Airports table due to duplicate IATA codes. | Sprint 1 | Backend Team | Functional | Added unique constraint and cleaned seed data in seed_airports.py. | 21-11-2025 | Closed | Seeding successful.
2 | 24-11-2025 | Pricing service returned 500 error when demand_score was null. | Sprint 1 | Backend Team | Logic | Added default value handling in demand_factor calculation. | 25-11-2025 | Closed | Calculation robust.
3 | 29-11-2025 | Search button unclickable on mobile devices due to z-index overlap. | Sprint 2 | Backend Team | Security/DB | Adjusted CSS z-index and padding in page.tsx Hero section. | 30-11-2025 | Closed | Button works on mobile.
4 | 2025-02-12 | "Same-Day Surge" pricing not triggering for flights departing in < 4 hours. | Sprint 2 | Backend Team | Algorithmic | Fixed interval logic in sameday_factor function in pricing.py. | 2025-03-12 | Closed | Surge pricing verified.
5 | 2025-07-12 | Popular Routes images failed to load for "Bengaluru" (404 Error). | Sprint 3 | DevOps | Infrastructure | Corrected image path from bangalore.jpg to BLR.jpg in mapping. | 2025-08-12 | Closed | Images loading correctly.
6 | 2025-10-12 | Admin Dashboard logout didn't clear session cookies properly. | Sprint 3 | Backend Team | Concurrency | Updated logout endpoint to explicitly invalidate JWT cookies. | 2025-11-12 | Closed | Logout secure.
7 | 16-12-2025 | Flight Simulator caused DB locks preventing new bookings. | Sprint 4 | Frontend Team | UI/Validation | Reduced simulator write frequency and optimized transaction scope. | 17-12-2025 | Closed | No deadlocks observed.
8 | 23-12-2025 | Booking Confirmation email displayed raw HTML tags to user. | Sprint 5 | Backend Team | Logic | Switched to proper HTML email template rendering in email_service.py. | 24-12-2025 | Closed | Emails formatted clean.
9 | 30-12-2025 | Flight Card UI alignment broken on Safari for long city names. | Sprint 6 | Backend Team | Functional | Added text-truncate and flex-wrap properties to FlightCard.tsx. | 31-12-2025 | Closed | UI consistent.
10 | 2026-03-01 | "NaN" displayed for Total Price when infant count was > 2. | Sprint 6 | Frontend Team | UI | Fixed price multiplier logic for infants in frontend state. | 2026-04-01 | Closed | Price accurate.